## MVP_Project_Plan
Task ID | Task Name | Description | Start Date | End Date | Duration (Days) | Status
1 | Backend Setup & Database Modeling | Design schema, setup Postgres, create test data | 2025-07-28 | 2025-08-01 | 5 | Competed
2 | API Development | Implement endpoints for auth, KPIs, metrics | 2025-08-02 | 2025-08-08 | 7 | Competed
3 | Authentication & Role Management | JWT/session auth and role-based access | 2025-08-09 | 2025-08-11 | 3 | Competed
4 | Frontend Integration with Live Data | Connect frontend to backend APIs | 2025-08-12 | 2025-08-16 | 5 | Competed
5 | User Features for MVP | Create/assign KPIs, metric submission, dashboard views | 2025-08-17 | 2025-08-20 | 4 | Competed
6 | Admin/Manager Features | User/team management, templates, coaching | 2025-08-21 | 2025-08-25 | 5 | To Do
7 | Dashboard Polishing | Data refresh, sorting/filtering, visual tweaks | 2025-08-26 | 2025-08-28 | 3 | In Progress
8 | Testing & QA | Manual testing, UAT, bug fixing | 2025-08-29 | 2025-09-02 | 5 | To Do
9 | Pilot Deployment | Deploy frontend/backend, onboard pilot users | 2025-09-03 | 2025-09-06 | 4 | To Do
10 | Documentation | Dev guide, API docs, user how-to | 2025-09-07 | 2025-09-12 | 6 | To Do